Changing this number will scroll the Gantt Chart view.
Create a Project Schedule in this worksheet.
Enter title of this project in cell B1.
Information on how to use this worksheet, including instructions for screen readers and the author of this workbook, is in the About worksheet.

Enter Company name in cel B2.
Enter the name of the Project Lead in cell C3. Enter the Project Start date in cell Q1. Project Start: label is in cell I1.
The Display week in cell Q2 is the starting week to display in the project schedule in cell I4. The project start date is Week 1. To change the display week, enter a new week number in cell Q2.

Start date for each week is auto calculated starting in I4.
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date and are auto calculated.

Today's date is outlined from today's date in row 5 through the entire date column to the end of the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new title in cell B8.
To delete the phase and work only from tasks, simply delete this row.
B9 contains the task name. C9 is the assignee. D9 is a progress bar that shades based on the number entered into the cell.

E9 contains the start date and F9 contains the end date.

The Gantt chart will fill in starting in cell I9 based on task dates.
Rows 10 through 13 repeat the pattern from row 9.

Repeat the instructions from cell A9 for all task rows in this worksheet.

Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more.
Cell B14 contains the Phase 2 sample title. Enter a new title in cell B14.
To delete the phase and work only from tasks, simply delete this row. To remove the phase, simply delete the row. Add tasks to previous phase by entering a new row above this one.

Phase 3's sample block starts in cell B20.
Phase 4's sample block starts in cell B26.
This row marks the end of the Project Schedule. DO NOT enter anything in this row.
Insert new rows ABOVE this one to continue building out your Project Schedule.
## Project_schedule
	Security Monitoring with Graylog SIEM for Catnip Games International
						Display week:					1
	Project lead-Athena Parsa, Kanyin Sola, Niloofar Thaha, Mathew Faller					Project start:					Sat, 3/29/2025
						Mar 24, 2025					Mar 31, 2025					Apr 7, 2025					Apr 14, 2025					Apr 21, 2025					Apr 28, 2025					May 5, 2025					May 12, 2025
	TASK	ASSIGNED TO	PROGRESS	START	END			24	25	26	27	28	29	30	31	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18
						M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
	Initiation
	Setup log collection from development environments and network devices	Mathew Faller	100%	3/29/25	4/1/25		4
	Initial configuration of setup	Athena Parsa, Kanyin Sola, Niloofar Thaha, Mathew Faller	100%
	Configure log collection from game servers and authentication systems	Mathew Faller	100%	4/1/25	4/3/25		3
	Configure data retention policies and storage optimisation	Kanyin Sola	100%	4/3/25	4/7/25		5
	Performance testing and tuning of log ingestion pipeline	Mathew Faller	100%	4/7/25	4/12/25		6
	Implement log parsing and normalisation rules	Mathew Faller	100%	4/2/25	4/4/25		3
	Planning and design
	Design and create security overview dashboard for SOC team	Athena Parsa	100%	4/3/25	4/7/25		5
	Develop player authentication monitoring dashboard	Athena Parsa	100%	4/5/25	4/10/25		6
	Create DDoS detection and game server health dashboard	Mathew Faller	100%	4/10/25	4/13/25		4
	Implement development environment security dashboard	Athena Parsa	100%	4/10/25	4/12/25		3
	Architecture design and capacity planning for Graylog SIEM infrastructure	Athena Parsa	100%
	Setup network security monitoring dashboard with traffic analysis	Athena Parsa	100%	4/10/25	4/13/25		4
	Execution
	Develop correlation rules for unauthorised access detection	Athena Parsa	100%	4/13/25	4/18/25		6
	Create automation scripts for weekly security reports	Athena Parsa	100%	4/19/25	4/23/25		5
	Configure automated backup system and disaster recovery procedures	Athena Parsa	100%	4/24/25	4/29/25		6
	Implement DDoS attack detection rules	Mathew Faller	100%	4/30/25	5/4/25		5
	Setup alert routing and incident response workflow integration	Kanyin Sola	100%	4/24/25	4/28/25		5
	Evaluation
	W5 - Documentation finalisation and handover preparation	Niloofar Thaha	100%	4/15/25	4/18/25		4
	W5 - Security team training sessions	Niloofar Thaha	100%	4/18/25	4/22/25		5
	W5 - Load testing and performance validation	Kanyin Sola	100%	4/23/25	4/26/25		4
	W5 - Project sign-off and production deployment	Athena Parsa, Kanyin Sola, Niloofar Thaha, Mathew Faller	100%	4/20/25	4/23/25		4
	W5 - End-to-end testing of monitoring system	Kanyin Sola	100%	4/22/25	4/27/25		6

	Insert new rows ABOVE this one

## About
SIMPLE GANTT CHART by Vertex42.com

About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. / TimeSheet / About / The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. / This hidden text will not print. / To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.